## QA Dashboard
QA Test Execution Dashboard
Project / Release: |  | Agent Onboarding & Recruitment Support - UAT Sept 2026 (Automation) |  |  |  |  | Report date: |  | 2026-10-01
TOTAL TEST CASES |  |  | EXECUTION % |  |  | PASS % |  |  | HIGH / CRITICAL RISK
6 |  |  | 66.67% |  |  | 100% |  |  | 0
Test cases in repository |  |  | 4 of 6 test cases executed |  |  | Of executed test cases |  |  | Risk level High or Critical (P1 / P2)
PASSED |  |  | FAILED |  |  | BLOCKED |  |  | AUTOMATION CANDIDATES
4 |  |  | 0 |  |  | 0 |  |  | 3
67% of all test cases |  |  | 0% of all test cases |  |  | 0% of all test cases |  |  | 50% of all test cases
Risk Distribution |  |  | Test Status |  |  | Execution by Tester
Risk Level | Test Cases | % of Total | Status | Test Cases | % of Total | Executed By |  | Assigned | Executed | Execution % | Pending
Critical | 0 | 0% | Pass | 4 | 66.67% | Aishwarya |  | 6 | 6 | 100% | 0
High | 0 | 0% | Fail | 0 | 0%
Medium | 0 | 0% | Blocked | 0 | 0%
Low | 6 | 100% | Not Run | 0 | 0%
Total | 6 | 100% | Not Applicable | 0 | 0%
|  |  | Invalid | 2 | 33.33%
Total |  |  |  | 6 | 100%
[6 empty] | Total |  | 6 | 6 | 100% | 0
Test Cases by Risk Level | [5 empty] | Test Execution Status
Definitions & Notes
Execution % = (Passed + Failed + Blocked) ÷ Total Test Cases. Pass % = Passed ÷ (Passed + Failed + Blocked).
Risk Score = Impact (Low 1 … Critical 4) × Likelihood (Rare 1 … Almost Certain 5). Risk Level: Critical ≥ 12, High 8–11, Medium 4–7, Low < 4.
Priority follows Risk Level: Critical = P1, High = P2, Medium = P3, Low = P4. High / Critical Risk counts P1 + P2 test cases.
All figures are calculated live from the 'Test Cases' sheet (rows 2–501). Enter tester names in the shaded 'Executed By' cells above (up to 9); enter Project / Release in the shaded field at the top.

## Test Cases
Test Case ID | Module / Feature | Requirement ID / User Story | Test Case Description | Test Type | Test Steps | Expected Result | Actual Result | Status | Business Criticality (Business importance) | Impact (Business/customer impact) | Likelihood (Probability of failure) | Risk Score (Impact * Likelihood) | Risk Level (Risk if functionality fails) | Priority (Execution priority) | Scope Category | Automation Candidate | Regression Candidate | Environment | Defect ID | Executed By | Execution Date | Remarks
RLC_CS_008 | Campaign Summary | TS: Campaign Summary | Verify campaign chronological ordering. | UI | 1. Precondition: at least three campaigns with different creation dates exist. 2. Navigate to https://192.168.2.80:8443 and log in as AA (102186). 3. Click Recruitment Leads Mgmt > Campaign Management. 4. Note the order of campaigns in the list. 5. Verify campaigns are displayed in the required chronological (date) order. | Campaigns are displayed in the required chronological order. | Campaigns are displayed in the required chronological order. | Pass | Low | Low | Unlikely | 2 | Low | P4 | Optional | Yes | No | UAT |  | Aishwarya | 2026-10-01
RLC_DM_006 | Document Management | TS: Document Management | Verify document viewing without download. | Functional | 1. Precondition: a document has been uploaded for a lead. 2. Navigate to https://192.168.2.80:8443 and log in as HOB/AH (102117). 3. Click Recruitment Leads Mgmt and select a campaign in Ongoing status assigned to branch WD01. 4. Open the lead and click the view (eye) icon of the document. 5. Check whether a download option is available. 6. Verify the document can be viewed and download is not offered (download is not supported). | Documents can be viewed; document download is not expected as supported functionality. | Documents can be viewed; document download is not expected as supported functionality. | Pass | Low | Low | Unlikely | 2 | Low | P4 | Optional | Yes | No | UAT |  | Aishwarya | 2026-10-01
RLC_BL_003 | Blacklisting | TS: Blacklisting Upload & View | Verify blacklist upload instructions. | UI | 1. Navigate to https://192.168.2.80:8443 and log in as Agency Admin (102186) 2. Click the Blacklisting card 3. Review the Upload Blacklisting section 4. Verify the applicable blacklist upload instructions are displayed | Applicable blacklist upload instructions are displayed. | Applicable blacklist upload instructions are displayed. | Pass | Low | Low | Rare | 1 | Low | P4 | Optional | Yes | No | UAT |  | Aishwarya | 2026-10-01
RLC_GV_007 | General Validation | TS: General Validations – UI Consistency | Verify Campaign Cost/Budget terminology. | UI | 1. Navigate to https://192.168.2.80:8443 and log in as Agency Admin (102186) 2. Click Recruitment Leads Mgmt > Campaign Management and click '+' 3. Note the Cost/Budget label on the create form 4. Check the same label on the edit form, campaign list and campaign summary 5. Verify Campaign Cost/Budget terminology is consistent across applicable screens | Campaign Cost/Budget terminology is consistent with the implemented requirement across applicable screens. | Campaign Cost/Budget terminology is consistent with the implemented requirement across applicable screens. | Pass | Low | Low | Rare | 1 | Low | P4 | Optional | No | No | UAT |  | Aishwarya | 2026-10-01
RLC_GV_011 | General Validation | TS: Document Management – Multi-language | Verify multi-language document scope. | Functional | 1. Navigate to https://192.168.2.80:8443 and log in as Agency Admin (102186) 2. Open the document upload/view area 3. Upload/view a Sinhala or Tamil document 4. Verify multi-language document rendering/download is not treated as an expected functional requirement | Multi-language document rendering/download is not treated as an expected functional requirement. | Not executed: Marked 'Not in scope' by ASPL in the test scenario document; there is no functional behaviour to automate. | Invalid | Low | Low | Rare | 1 | Low | P4 | Out of Scope | No | No | UAT |  | Aishwarya | 2026-10-01
RLC_GV_012 | General Validation | TS: User Wise – Marketing/AA | Verify annual NIC data cleansing scope. | Functional | 1. Navigate to https://192.168.2.80:8443 and log in as Agency Admin (102186) 2. Review the available lead/NIC maintenance functions 3. Check whether any annual NIC data cleansing option or job is exposed 4. Verify annual NIC data cleansing is not treated as an in-scope test expectation | Annual data cleansing for existing NIC is not treated as an in-scope functional test expectation. | Not executed: Marked 'Not in scope' by ASPL in the test scenario document; there is no functional behaviour to automate. | Invalid | Low | Low | Rare | 1 | Low | P4 | Out of Scope | No | No | UAT |  | Aishwarya | 2026-10-01

## Lists
Test Type | Business Criticality | Impact | Likelihood | Scope Category | Status | Priority | Yes/No | Environment | Release | Requirement Type
Functional | Low | Low | Rare | Core | Not Run | P1 | Yes | DEV | Release 1 | Functional
Regression | Medium | Medium | Unlikely | Impacted | Pass | P2 | No | QA | Release 2 | Non-Functional
Integration | High | High | Possible | Regression | Fail | P3 |  | UAT | Release 3 | Technical
API | Critical | Critical | Likely | Integration | Blocked | P4 |  | Production |  | Business
UI |  |  | Almost Certain | Security | Not Applicable
Mobile |  |  |  | Performance | Invalid
Performance |  |  |  | Optional
Security |  |  |  | Out of Scope
UAT
Smoke
Sanity
Note: Scope category descriptions
Core – Mandatory functionality
Impacted – Directly affected by the change
Regression – Existing functionality potentially affected
Integration – External/system integration
Security – Security-sensitive functionality
Performance – Performance-sensitive functionality
Optional – Lower-priority validation
Out of Scope – Explicitly excluded with justification
Testcase column color code
Manual Entry
Dropdown Selection
Values Based on Calculation