## QA Dashboard
QA Test Execution Dashboard
Project / Release: |  | Agent Onboarding & Recruitment Support – UAT Sept 2026 |  |  |  |  | Report date: |  | 2026-09-30
TOTAL TEST CASES |  |  | EXECUTION % |  |  | PASS % |  |  | HIGH / CRITICAL RISK
2 |  |  | 100% |  |  | 50% |  |  | 0
Test cases in repository |  |  | 2 of 2 test cases executed |  |  | Of executed test cases |  |  | Risk level High or Critical (P1 / P2)
PASSED |  |  | FAILED |  |  | BLOCKED |  |  | AUTOMATION CANDIDATES
1 |  |  | 1 |  |  | 0 |  |  | 0
50% of all test cases |  |  | 50% of all test cases |  |  | 0% of all test cases |  |  | 0% of all test cases
Risk Distribution |  |  | Test Status |  |  | Execution by Tester
Risk Level | Test Cases | % of Total | Status | Test Cases | % of Total | Executed By |  | Assigned | Executed | Execution % | Pending
Critical | 0 | 0% | Pass | 1 | 50% | Anagha |  | 1 | 1 | 100% | 0
High | 0 | 0% | Fail | 1 | 50% | Nikhil |  | 1 | 1 | 100% | 0
Medium | 1 | 50% | Blocked | 0 | 0%
Low | 1 | 50% | Not Run | 0 | 0%
Total | 2 | 100% | Not Applicable | 0 | 0%
Total |  |  |  | 2 | 100%
[6 empty] | Total |  | 2 | 2 | 100% | 0
Test Cases by Risk Level | [5 empty] | Test Execution Status
Definitions & Notes
Execution % = (Passed + Failed + Blocked) ÷ Total Test Cases. Pass % = Passed ÷ (Passed + Failed + Blocked).
Risk Score = Impact (Low 1 … Critical 4) × Likelihood (Rare 1 … Almost Certain 5). Risk Level: Critical ≥ 12, High 8–11, Medium 4–7, Low < 4.
Priority follows Risk Level: Critical = P1, High = P2, Medium = P3, Low = P4. High / Critical Risk counts P1 + P2 test cases.
All figures are calculated live from the 'Test Cases' sheet (rows 2–501). Enter tester names in the shaded 'Executed By' cells above (up to 9); enter Project / Release in the shaded field at the top.

## Test Cases
Test Case ID | Module / Feature | Requirement ID / User Story | Test Case Description | Test Type | Test Steps | Expected Result | Actual Result | Status | Business Criticality (Business importance) | Impact (Business/customer impact) | Likelihood (Probability of failure) | Risk Score (Impact * Likelihood) | Risk Level (Risk if functionality fails) | Priority (Execution priority) | Scope Category | Automation Candidate | Regression Candidate | Environment | Defect ID | Executed By | Execution Date | Remarks
AA_CAM_001 | AA Process | RLM: Create a Campaign | Verify Agency Admin can create a campaign by providing all valid mandatory campaign details. | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as AA (102186) 3. Click Recruitment Leads Mgmt > Campaign Management and click '+' 4. Enter a unique Campaign Name, select Start Date earlier than End Date, enter Campaign Budget and Lead Target (< 500) 5. Click Proceed and then OK 6. Verify the campaign is created successfully and is listed in the campaign list | Campaign is created successfully and becomes available in the campaign list. |  | Not Run | High | High | Unlikely |  |  |  | Core | Yes | Yes | UAT
AA_CAM_002 | AA Process | TS: HOB/Agency Supervisor Role | Verify a campaign created by Agency Admin is visible to all HOBs and AS users. | Functional | 1. Precondition: AA (102186) has created an active campaign assigned to branch WD01 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Recruitment Leads Mgmt and verify the new campaign is listed 5. Logout and login as AS (102119) 6. Click Recruitment Leads Mgmt 7. Verify the newly created campaign is available to both HOB and AS users | Newly created campaign is available to all authorized HOB and AS users. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
AA_CAM_003 | AA Process | TS: User Wise–Marketing/AA | Verify Agency Admin can deactivate an active campaign. | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as AA (102186) 3. Click Recruitment Leads Mgmt > Campaign Management 4. Locate an Active campaign and click the 3 dots menu 5. Click Deactivate and confirm with OK 6. Logout and login as HOB (102117) and open Recruitment Leads Mgmt 7. Verify campaign status changes to Inactive and no new leads/transactions can be added to it | Campaign status changes from Active to Inactive successfully. The deactivated campaign is no longer available for new campaign-related transactions as per business rules. |  | Not Run | High | High | Unlikely |  |  |  | Core | Yes | Yes | UAT
AA_LEAD_004 | AA Process | TS: Lead Bulk Upload | Verify Agency Admin can upload a valid bulk lead Excel file against an active campaign. | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as AA (102186) 3. Click Recruitment Leads Mgmt, click the 3 dots on an Active campaign and select Bulk 4. Click Download Sample Template and save the file 5. Replace sample data with unique Sri Lankan leads (Name, NIC, Contact Number, Branch mandatory) and save as .xlsx 6. Upload the file via 'Please upload .XLS, .XLSX or .CSV files only', click Bulk Upload bulk leads and click OK 7. Verify the upload success message and that valid leads are associated with the selected campaign | Bulk lead file is uploaded successfully and valid leads are associated with the selected campaign. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
AA_SLII_005 | AA Process | US 1.5 | Verify Agency Admin can upload a valid SLII Exam Bulk Excel file. | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as AA (102186) 3. Click Recruitment Leads Mgmt > SLII Exam Management 4. Click Download Sample Template and save the file 5. Fill valid SLII exam data for Sri Lankan candidates (unique NICs) and save as .xlsx 6. Upload the file via 'Please upload .xlsx or .xls or .csv files only', click Upload and click OK 7. Verify the success message and that the file appears in the Uploaded SLII Exam Result list | SLII exam data is uploaded successfully and becomes available for use during agent onboarding. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
AA_SLII_006 | AA Process | US 1.5 | Verify uploaded SLII exam data is correctly retrieved during onboarding for the corresponding agent. | Integration | 1. Precondition: SLII exam file uploaded by AA containing a record for the candidate NIC; lead for that NIC is proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Navigate through the form to the Qualification & Examination Details section 6. Verify the IBSL/SLII examination data is auto-populated and matches the uploaded record for that NIC | System retrieves the applicable SLII exam information and uses it during agent onboarding. |  | Not Run | High | High | Possible |  |  |  | Integration | Yes | Yes | UAT
AA_BL_007 | AA Process | RLM: Blacklisting | Verify Agency Admin can upload a valid Blacklisted Agents Excel file. | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as AA (102186) 3. Click the Blacklisting card 4. Click Download Sample Template and save the file 5. Fill blacklisted agent records with Sri Lankan data (NIC etc.) and save 6. Upload the file via 'Please upload .xlsx or .xls or .csv files only', click Upload and click OK 7. Verify the file is uploaded successfully and the records are available for blacklist validation | Blacklisted agent records are uploaded successfully and become available for blacklist validation. |  | Not Run | Critical | High | Possible |  |  |  | Core | Yes | Yes | UAT
AA_AGENT_008 | AA Process | AO Flow §1 Agent Onboarding–AA | Verify Agency Admin can create an agent by entering valid agent details. | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as AA (102186) 3. Click Agent Management > Agent Onboarding and click '+' 4. Select NIC, enter a valid unique Sri Lankan NIC (age 18–65) and click Proceed 5. Complete applicant details, upload documents, nationality/language, unique contact details and address 6. Select organisational details (Group ST, Cluster CC/DH, Branch WD01, Unit WD0100) and bank details with a unique account number 7. Upload the bank document, click Submit and click OK 8. Verify the agent is created successfully with a unique agent/sales code | Agent is created successfully with a unique agent/sales code. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
AA_AGENT_009 | AA Process | AO Flow §1 Agent Onboarding–AA | Verify Agency Admin can select any available branch while creating an agent. | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as AA (102186) 3. Click Agent Management > Agent Onboarding and click '+'; start NIC onboarding with a unique Sri Lankan NIC 4. Complete applicant, document, personal and contact details 5. On organisational details open the Branch dropdown and select a branch other than WD01 6. Complete bank details, click Submit and click OK 7. Verify the selected branch is assigned to the newly created agent | Selected branch is successfully assigned to the newly created agent. |  | Not Run | Medium | Medium | Possible |  |  |  | Core | Yes | No | UAT
AA_AGENT_010 | AA Process | AO Flow §1 Agent Onboarding–AA | Verify sales code is activated automatically after successful agent creation by Agency Admin. | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as AA (102186) 3. Create an agent via Agent Management > Agent Onboarding > '+' with valid unique Sri Lankan data and click Submit > OK 4. Note the generated sales code and check its status in the agent list 5. Logout and login with the new agent's credentials 6. Verify the sales code is active without additional approval and the agent logs in successfully | Sales code is activated directly without additional approval, and the newly created agent can log in successfully. |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_002 | RS Approval | RLM: Recruitment Support–HOB Flow | Verify TRSM (Immediate Supervisor) interview approval for candidate age >= 22 | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as HOB (102117) 3. Click Recruitment Leads Mgmt, select an Ongoing campaign and click '+' 4. Fill the lead form with unique Sri Lankan NIC (candidate age ≥ 22), name, contact number and branch 5. Set interview status 'Agreed for the interview', schedule date = current date, enter remark, click Approved and click OK 6. Logout and login as Immediate Supervisor/TRSM (102118), open Approval Tray, select the lead, select current date, enter remark, click Approve and click OK 7. Verify the TRSM (Immediate Supervisor) approves the interview successfully | TRSM (Immediate Supervisor) should be able to approve the interview successfully |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_003 | RS Approval | RLM: Recruitment Support–HOB Flow | Verify onboarding eligibility for candidate age >= 22 after TRSM (Immediate Supervisor) approval | Functional | 1. Precondition: lead with candidate age ≥ 22 approved by HOB and TRSM (102118) 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Recruitment Leads Mgmt and click Proceed on the approved lead 5. Click Agent Management > Agent Onboarding and click Edit on the New Lead 6. Logout and verify AS (102119) and LOP (102043) can also open the onboarding form for the lead 7. Verify HOB can proceed the lead to onboarding and HOB, AS and LOP can fill the onboarding form | HOB should be able to proceed the lead to onboarding and HOB, AS, LOP should be able to fill the onboarding form |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_004 | RS Approval | RLM: Recruitment Support–HOB Flow | Verify interview approval flow for candidate age < 22 after HOB approval | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as HOB (102117) 3. Click Recruitment Leads Mgmt, select an Ongoing campaign and click '+' 4. Fill the lead form with unique Sri Lankan NIC (candidate age < 22), name, contact number and branch 5. Select the supporting document type (e.g. Prospect 100, Field Visit) and upload a PDF/PNG/JPG file under 10 MB 6. Set interview status 'Agreed for the interview', schedule date = current date, enter remark, click Approved and click OK 7. Logout and login as Immediate Supervisor/TRSM (102118) and open Approval Tray 8. Verify the lead appears in the TRSM interview approval bucket | After HOB approval, the lead should appear in TRSM interview approval bucket |  | Not Run | Critical | Critical | Likely |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_005 | RS Approval | RLM: Recruitment Support–HOB Flow | Verify Agency Admin approval flow for candidate age < 22 | Functional | 1. Precondition: lead with candidate age < 22 approved by HOB (102117) 2. Navigate to https://192.168.2.80:8443 3. Logout and login as Immediate Supervisor/TRSM (102118), open Approval Tray, select the lead, select current date, enter remark, click Approve and click OK 4. Logout and login as AA (102186) and open Approval Tray 5. Verify the lead appears in the Agency Admin approval bucket | After TRSM approval, the lead should appear in Agency Admin approval bucket |  | Not Run | Critical | Critical | Likely |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_006 | RS Approval | RLM: Recruitment Support–HOB Flow | Verify final approval by Agency Admin for candidate age < 22 | Functional | 1. Precondition: lead with candidate age < 22 approved by HOB and TRSM 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray and select the recently approved lead 5. Select interview schedule date = current date, enter remark, click Approved and click OK 6. Verify Agency Admin approves the lead successfully | Agency Admin should be able to approve the lead successfully |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_007 | RS Approval | RLM: Recruitment Support–HOB Flow | Verify onboarding eligibility for candidate age < 22 after Agency Admin approval | Functional | 1. Precondition: lead with candidate age < 22 approved by HOB, TRSM and AA 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Recruitment Leads Mgmt and click Proceed on the approved lead 5. Click Agent Management > Agent Onboarding and click Edit on the New Lead 6. Logout and verify AS (102119) and LOP (102043) can also open the onboarding form 7. Verify HOB can proceed the lead to onboarding and HOB, AS and LOP can fill the onboarding form | HOB should be able to proceed the lead to onboarding and HOB, AS, and LOP should be able to fill the onboarding form |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_008 | RS Approval | TS: Approval Tray | Verify rejection by HOB during interview approval | Functional | 1. Navigate to https://192.168.2.80:8443 2. Login as HOB (102117) 3. Click Recruitment Leads Mgmt, select an Ongoing campaign and click '+' 4. Fill the lead form with unique Sri Lankan NIC (candidate age ≥ 22), name, contact number and branch 5. Set interview status to reject the interview, enter remark, click Reject and click OK 6. Logout and login as Immediate Supervisor/TRSM (102118) and open Approval Tray 7. Verify the lead is rejected immediately and does not appear in any further approval stage | Lead should be rejected immediately and no further approval stages should be triggered |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_009 | RS Approval | TS: Approval Tray | Verify rejection by TRSM (Immediate Supervisor) during interview approval | Functional | 1. Precondition: lead (age < 22) approved by HOB and pending with TRSM 2. Navigate to https://192.168.2.80:8443 3. Logout and login as Immediate Supervisor/TRSM (102118), open Approval Tray, select the lead, select current date, enter remark, click Reject and click OK 4. Logout and login as AA (102186) and open Approval Tray 5. Login as HOB (102117) and check the lead in Recruitment Leads Mgmt 6. Verify the lead is rejected and does not proceed to Agency Admin or onboarding | Lead should be rejected immediately and should not proceed to Agency Admin or onboarding |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_010 | RS Approval | TS: Approval Tray | Verify rejection by Agency Admin for candidate age < 22 | Functional | 1. Precondition: lead (age < 22) approved by HOB and TRSM, pending with AA 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray, select the lead, enter remark, click Reject and click OK 5. Logout and login as HOB (102117) and open Recruitment Leads Mgmt 6. Verify the lead is rejected immediately and is not available to proceed to onboarding | Lead should be rejected immediately and should not proceed to onboarding |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_011 | RS Approval | TS: Lead Management | Verify lead status after rejection at any stage | Functional | 1. Precondition: leads rejected at HOB, TRSM and AA stages 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Recruitment Leads Mgmt and open the campaign containing the rejected leads 5. Check the status and available actions for each rejected lead 6. Verify status is displayed as 'Rejected' and no further actions (Edit/Proceed/Approve) are available | Lead status should be displayed as "Rejected" and no further actions should be available |  | Not Run | High | Medium | Possible |  |  |  | Core | Yes | No | UAT
TC_REC_APP_012 | RS Approval | TS: Lead Management | Verify HOB & AS can initiate onboarding only after completion of all required interview approvals | Functional | 1. Precondition: lead approved by HOB but pending with TRSM 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Recruitment Leads Mgmt and verify Proceed is not available for the pending lead 5. Logout and login as AS (102119) and verify the same 6. Complete all remaining approvals (TRSM, and AA if age < 22) 7. Logout and login as HOB (102117) and open Recruitment Leads Mgmt 8. Verify proceeding to onboarding is allowed only after all mandatory approvals are completed | System should allow proceeding to onboarding only after all mandatory approvals are completed |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_013 | RS Approval | AO Flow §2 Agent Onboarding–AH/HOB | Verify AS can fill onboarding form after successful interview approvals | Functional | 1. Precondition: lead fully approved and proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as AS (102119) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) as calculated, select PEP Question, click Raise Request and click OK 7. Verify AS can access and submit onboarding details for the approved lead (Raise Request) | AS should be able to access and submit onboarding details for the approved lead (Raise Request) |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_014 | RS Approval | AO Flow §2 Agent Onboarding–AH/HOB | Verify LOP can fill onboarding form after successful interview approvals | Functional | 1. Precondition: lead fully approved; HOB or AS has clicked Proceed on the lead 2. Navigate to https://192.168.2.80:8443 3. Login as LOP (102043) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) as calculated, select PEP Question, click Raise Request and click OK 7. Verify LOP can submit onboarding details (Raise Request) only after HOB/AS has proceeded the lead | LOP should be able to access and submit onboarding details for the approved lead (Raise Request) but First AS or HOB should proceed the lead. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_REC_APP_015 | RS Approval | AO Flow §2 Agent Onboarding–AH/HOB | Verify HOB can fill onboarding form after successful interview approvals | Functional | 1. Precondition: lead fully approved and proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) as calculated, select PEP Question, click Raise Request and click OK 7. Verify HOB can access and submit onboarding details for the approved lead (Raise Request) | HOB should be able to access and submit onboarding details for the approved lead (Raise Request) |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
INT_NOTIF_001 | RS Notification | TS: Approvals | Verify notification is sent to TRSM when HOB approves the interview status and the application moves to TRSM approval. | Integration | 1. Navigate to https://192.168.2.80:8443 2. Login as HOB (102117) 3. Click Recruitment Leads Mgmt, select an Ongoing campaign and click '+' 4. Fill the lead form with unique Sri Lankan NIC (candidate age < 22), name, contact number and branch 5. Set interview status 'Agreed for the interview', schedule date = current date, enter remark, click Approved and click OK 6. Logout and login as Immediate Supervisor/TRSM (102118) 7. Open the notification panel (bell icon) and open Approval Tray 8. Verify the application is in the TRSM bucket and TRSM receives the approval notification | Application moves to TRSM bucket and TRSM receives the approval notification. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_002 | RS Notification | TS: Approvals | Verify notification is sent to AA when TRSM approves the application. | Integration | 1. Precondition: lead (age < 22) approved by HOB, pending with TRSM 2. Navigate to https://192.168.2.80:8443 3. Logout and login as Immediate Supervisor/TRSM (102118), open Approval Tray, select the lead, select current date, enter remark, click Approve and click OK 4. Logout and login as AA (102186) 5. Open the notification panel (bell icon) and open Approval Tray 6. Verify the application is in the AA bucket and AA receives the approval notification | Application moves to AA bucket and AA receives the approval notification. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_003 | RS Notification | TS: Approvals | Verify notification is sent to HOB when TRSM rejects the application. | Integration | 1. Precondition: lead approved by HOB, pending with TRSM 2. Navigate to https://192.168.2.80:8443 3. Logout and login as Immediate Supervisor/TRSM (102118), open Approval Tray, select the lead, select current date, enter remark, click Reject and click OK 4. Logout and login as HOB (102117) 5. Open the notification panel (bell icon) 6. Verify the application is Rejected at TRSM level and the HOB notification identifies TRSM as the rejection level | Application is marked Rejected at TRSM level and HOB receives a notification identifying TRSM as the rejection level. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_004 | RS Notification | TS: Approvals | Verify HOB receives the notification when TRSM rejects the application. | Integration | 1. Precondition: lead approved by HOB, pending with TRSM 2. Navigate to https://192.168.2.80:8443 3. Logout and login as Immediate Supervisor/TRSM (102118), open Approval Tray, select the lead, select current date, enter remark, click Reject and click OK 4. Logout and login as HOB (102117) 5. Open the notification panel (bell icon) 6. Verify HOB receives a notification that TRSM rejected the lead | HOB gets the notification when TRSM rejects the Lead. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_005 | RS Notification | TS: Approvals | Verify notification is sent to HOB when AA rejects the application. | Integration | 1. Precondition: lead (age < 22) approved by HOB and TRSM, pending with AA 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray, select the lead, enter remark, click Reject and click OK 5. Logout and login as HOB (102117) 6. Open the notification panel (bell icon) 7. Verify the application is Rejected at AA level and the HOB notification identifies AA as the rejection level | Application is marked Rejected at AA level and HOB receives a notification identifying AA as the rejection level. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_006 | RS Notification | TS: Approvals | Verify HOB can identify the exact approval level at which the application was rejected. | Integration | 1. Precondition: two leads (age < 22) approved by HOB 2. Navigate to https://192.168.2.80:8443 3. Reject lead 1 at TRSM (102118) via Approval Tray 4. Approve lead 2 at TRSM and reject it at AA (102186) via Approval Tray 5. Logout and login as HOB (102117) 6. Open the notification panel (bell icon) and read both rejection notifications 7. Verify each notification clearly identifies whether the rejection occurred at TRSM or AA level | Notification clearly identifies whether rejection occurred at TRSM or AA level. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_007 | RS Notification | TS: Approvals | Verify approval notifications are sent only to the respective pending approver. | Integration | 1. Navigate to https://192.168.2.80:8443 2. Login as HOB (102117), create a lead (age < 22) and approve it 3. Logout and login as Immediate Supervisor/TRSM (102118) and check the notification panel 4. Logout and login as AA (102186) and confirm no notification yet for the lead 5. Login as TRSM, approve the lead 6. Logout and login as AA (102186) and check the notification panel 7. Verify TRSM is notified while pending with TRSM and AA is notified only when it reaches AA | TRSM receives notification when the application is pending with TRSM, and AA receives notification when it reaches AA. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_008 | RS Notification | TS: Approvals | Verify AA does not receive an approval notification before TRSM approves the application. | Integration | 1. Precondition: lead (age < 22) approved by HOB, pending with TRSM 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open the notification panel (bell icon) and open Approval Tray 5. Confirm no notification/tray item exists for the lead 6. Logout and login as Immediate Supervisor/TRSM (102118), open Approval Tray, select the lead, select current date, enter remark, click Approve and click OK 7. Logout and login as AA (102186) and check notifications 8. Verify AA notification is triggered only after TRSM approval and movement to the AA bucket | AA notification is triggered only after successful TRSM approval and application movement to AA bucket. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_009 | RS Notification | TS: Approvals | Verify application rejection at AA stops further processing. | Integration | 1. Precondition: lead (age < 22) pending with AA 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray, select the lead, enter remark, click Reject and click OK 5. Check notifications for TRSM (102118) and AA 6. Logout and login as HOB (102117) and check notifications 7. Verify the application remains rejected, no further approval notification is generated and HOB receives the AA rejection notification | Application remains rejected and no further approval notification is generated. HOB receives AA rejection notification. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
INT_NOTIF_010 | RS Notification | TS: Approvals | Verify approval/rejection notification contains the correct application/lead details. | Integration | 1. Precondition: leads approved and rejected at different stages 2. Navigate to https://192.168.2.80:8443 3. Login as each recipient (TRSM 102118, AA 102186, HOB 102117) 4. Open the notification panel (bell icon) and open each approval/rejection notification 5. Compare the applicant name/lead reference and status with the lead record 6. Verify each notification contains the correct applicant/lead reference and current approval/rejection status | Notification contains the correct applicant/lead reference and current approval/rejection status. |  | Not Run | Medium | Medium | Possible |  |  |  | Integration | Yes | No | UAT |  |  |  | Per ASPL test scenario doc: notifications are provided without remarks
INT_NOTIF_011 | RS Notification | TS: Approvals | Verify rejection at each approval stage: TRSM rejection and AA rejection. | Integration | 1. Precondition: two leads (age < 22) approved by HOB 2. Navigate to https://192.168.2.80:8443 3. Reject lead 1 at TRSM (102118) 4. Approve lead 2 at TRSM and reject it at AA (102186) 5. Logout and login as HOB (102117) 6. Open the notification panel (bell icon) 7. Verify both applications are rejected and HOB receives notifications specifying the exact rejection level | In either case, application is rejected and HOB receives notification specifying the exact rejection level. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
TC_ONB_001 | AO Approval | AO Flow §3 Approval Routing | Verify HOB can raise onboarding request when ARI < 30 | Functional | 1. Precondition: lead fully approved and proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) < 30, select PEP Question, click Raise Request and click OK 7. Logout and login as SMBD/Sr MBD (102118) and open Approval Tray 8. Verify the request is raised successfully and appears in the Sr MBD approval bucket | Request should be raised successfully and should appear in Sr MBD approval bucket |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_002 | AO Approval | AO Flow §3 Approval Routing | Verify AS can raise onboarding request when ARI < 30 | Functional | 1. Precondition: lead fully approved and proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as AS (102119) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) < 30, select PEP Question, click Raise Request and click OK 7. Logout and login as SMBD/Sr MBD (102118) and open Approval Tray 8. Verify the request is raised successfully and appears in the Sr MBD approval bucket | Request should be raised successfully and should appear in Sr MBD approval bucket |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_003 | AO Approval | AO Flow §3 Approval Routing | Verify LOP can raise onboarding request when ARI < 30 | Functional | 1. Precondition: lead fully approved and proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as LOP (102043) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) < 30, select PEP Question, click Raise Request and click OK 7. Logout and login as SMBD/Sr MBD (102118) and open Approval Tray 8. Verify the request is raised successfully and appears in the Sr MBD approval bucket | Request should be raised successfully and should appear in Sr MBD approval bucket |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_004 | AO Approval | AO Flow §3 Approval Routing | Verify approval flow for ARI < 30 | Functional | 1. Precondition: onboarding request with ARI < 30 raised by HOB 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Approve 4. Logout and login as LOP (102043) and verify the request is in Approval Tray 5. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Approve 6. Logout and login as AA (102186) and open Approval Tray 7. Verify after Sr MBD approval the request moves to LOP and after LOP approval to the Agency Admin bucket | After Sr MBD approval, request should move to LOP approval bucket and then to Agency Admin approval bucket |  | Not Run | Critical | Critical | Likely |  |  |  | Core | Yes | Yes | UAT
TC_ONB_005 | AO Approval | AO Flow §3 Approval Routing | Verify document upload accessibility after Agency Admin approval for ARI < 30 | Functional | 1. Precondition: onboarding request with ARI < 30 approved by AA 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Submitted and click the Edit icon for the application 5. Download the Agreement, upload the signed Agreement and click Submit 6. Repeat access check for AS (102119) and LOP (102043) on their own requests 7. Verify HOB, AS and LOP can upload the document and raise the activation request | HOB, AS and LOP should be able to upload document and raise activation request |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_006 | AO Approval | AO Flow §5 Final AA Approval | Verify sales code activation for ARI < 30 cases | Functional | 1. Precondition: ARI < 30 request approved by SMBD, LOP and AA; signed Agreement uploaded and activation request raised 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray and select the activation request 5. Review the application and click Approve 6. Check the sales code status in the agent list / login with the agent code 7. Verify Agency Admin activates the code and the sales code becomes active | Agency Admin should activate the code and sales code should become active |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_007 | AO Approval | AO Flow §3 Approval Routing | Verify HOB can raise onboarding request when ARI >= 30 | Functional | 1. Precondition: lead fully approved and proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) ≥ 30, select PEP Question, click Raise Request and click OK 7. Logout and login as LOP (102043) and open Approval Tray 8. Verify the request is raised successfully and appears in the LOP approval bucket | Request should be raised successfully and should appear in LOP approval bucket |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_008 | AO Approval | AO Flow §3 Approval Routing | Verify AS can raise onboarding request when ARI >= 30 | Functional | 1. Precondition: lead fully approved and proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as AS (102119) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) ≥ 30, select PEP Question, click Raise Request and click OK 7. Logout and login as LOP (102043) and open Approval Tray 8. Verify the request is raised successfully and appears in the LOP approval bucket | Request should be raised successfully and should appear in LOP approval bucket |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_009 | AO Approval | AO Flow §3 Approval Routing | Verify LOP can raise onboarding request when ARI >= 30 | Functional | 1. Precondition: lead fully approved and proceeded to onboarding 2. Navigate to https://192.168.2.80:8443 3. Login as LOP (102043) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) ≥ 30, select PEP Question, click Raise Request and click OK 7. Logout and login as LOP (102043) and open Approval Tray 8. Verify the request is raised successfully and appears in the LOP approval bucket | Request should be raised successfully and should appear in LOP approval bucket |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_010 | AO Approval | AO Flow §3 Approval Routing | Verify approval flow for ARI >= 30 | Functional | 1. Precondition: onboarding request with ARI ≥ 30 raised by HOB 2. Navigate to https://192.168.2.80:8443 3. Login as SMBD/Sr MBD (102118) and verify the request is NOT in Approval Tray 4. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Approve 5. Logout and login as AA (102186) and open Approval Tray 6. Verify after LOP approval the request moves to the Agency Admin approval bucket | After LOP approval, request should move to Agency Admin approval bucket |  | Not Run | Critical | Critical | Likely |  |  |  | Core | Yes | Yes | UAT
TC_ONB_011 | AO Approval | AO Flow §3 Approval Routing | Verify document upload accessibility after Agency Admin approval for ARI >= 30 | Functional | 1. Precondition: onboarding request with ARI ≥ 30 approved by AA 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Submitted and click the Edit icon for the application 5. Download the Agreement, upload the signed Agreement and click Submit 6. Repeat access check for AS (102119) and LOP (102043) on their own requests 7. Verify HOB, AS and LOP can upload the document and raise the activation request | HOB, AS and LOP should be able to upload document and raise activation request |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_012 | AO Approval | AO Flow §5 Final AA Approval | Verify sales code activation for ARI >= 30 cases | Functional | 1. Precondition: ARI ≥ 30 request approved by LOP and AA; signed Agreement uploaded and activation request raised 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray and select the activation request 5. Review the application and click Approve 6. Check the sales code status in the agent list / login with the agent code 7. Verify Agency Admin activates the code and the sales code becomes active | Agency Admin should activate the code and sales code should become active |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_013 | AO Approval | AO Flow §3 Approval Routing | Verify onboarding request raised for candidate age >= 50 | Functional | 1. Precondition: proceeded lead for a candidate aged ≥ 50 (Sri Lankan NIC) 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. Complete Applicant, Personal, Address, Qualification & Examination, Work Experience, Bank, Dependants and Witness details with valid unique Sri Lankan test data and required documents (< 10 MB) 6. On the Raise Request screen confirm Total (ARI) as calculated, select PEP Question, click Raise Request and click OK 7. Logout and login as LOP (102043) and open Approval Tray 8. Verify the request moves to the LOP approval bucket successfully | Request should move to LOP approval bucket successfully |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_014 | AO Approval | AO Flow §3 Approval Routing | Verify Medical Report option availability for candidate age >= 50 in the LOP approval tray | Functional | 1. Precondition: onboarding request for candidate aged ≥ 50 pending with LOP 2. Navigate to https://192.168.2.80:8443 3. Login as LOP (102043) 4. Open Approval Tray and select the application 5. Click Next to the document upload page 6. Verify the Medical Report upload option is displayed on the document upload page | Medical Report upload option should be displayed on the document upload page in the LOP approval tray |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_015 | AO Approval | AO Flow §3 Approval Routing | Verify approval flow for candidate age >= 50 | Functional | 1. Precondition: onboarding request for candidate aged ≥ 50 pending with LOP 2. Navigate to https://192.168.2.80:8443 3. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Approve 4. Logout and login as AA (102186) and open Approval Tray 5. Verify after LOP approval the request moves to the Agency Admin approval bucket | After LOP approval, request should move to Agency Admin approval bucket |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_016 | AO Approval | AO Flow §5 Final AA Approval | Verify sales code activation for candidate age >= 50 | Functional | 1. Precondition: request for candidate aged ≥ 50 approved by LOP and AA; signed Agreement uploaded and activation request raised 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray and select the activation request 5. Review the application and click Approve 6. Check the sales code status in the agent list / login with the agent code 7. Verify Agency Admin activates the code and the sales code becomes active | Agency Admin should activate the code and sales code should become active |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_017 | AO Approval | AO Flow §4 Approval Process | Verify rejection by Sr MBD for ARI < 30 case | Functional | 1. Precondition: onboarding request with ARI < 30 pending with Sr MBD 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Login as LOP (102043) and AA (102186) and check Approval Tray 5. Verify the request is rejected and does not proceed to LOP or Agency Admin | Request should be rejected and should not proceed to LOP or Agency Admin |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_018 | AO Approval | AO Flow §4 Approval Process | Verify rejection by LOP during onboarding approval | Functional | 1. Precondition: onboarding request pending with LOP 2. Navigate to https://192.168.2.80:8443 3. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as AA (102186) and check Approval Tray 5. Verify the request is rejected and no further processing happens | Request should be rejected and no further processing should happen |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_019 | AO Approval | AO Flow §5 Final AA Approval | Verify rejection by Agency Admin during onboarding approval | Functional | 1. Precondition: onboarding request pending with AA 2. Navigate to https://192.168.2.80:8443 3. Logout and login as AA (102186), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Check the sales code status of the application 5. Verify the request is rejected and the sales code is not activated | Request should be rejected and sales code should not be activated |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_020 | AO Approval | AO Flow §4 Approval Process | Verify rejected onboarding case status | Functional | 1. Precondition: onboarding request rejected by an approver 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Agent Management > Agent Onboarding and locate the application 5. Check the status and try to raise an activation request 6. Verify status is displayed as 'Rejected' and the activation request is not allowed | Rejected case should not allow activation request and status should be displayed as "Rejected" |  | Not Run | High | Medium | Possible |  |  |  | Core | Yes | No | UAT
TC_ONB_021 | AO Approval | AO Flow §2 Agent Onboarding–AH/HOB | Verify the mandatory document page contains AS Regstraion field | Functional | 1. Precondition: proceeded lead available 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. In Applicant/Personal details select Designation = Agency Supervisor and click Next 6. Verify the mandatory document page shows the 'AS Registration' upload field | When we choose the designaition Agency Supervisor (In the personal details page) In the mandatry document page "AS Registration" field should be available to upload the document. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
TC_ONB_022 | AO Approval | AO Flow §2 Agent Onboarding–AH/HOB | Verify the mandatory document page contains AS Regstraion field and CRIB Report field. | Functional | 1. Precondition: proceeded lead available 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Agent Management > Agent Onboarding and click Edit on the New Lead 5. In Applicant/Personal details select Designation = Agency Head and click Next 6. Verify the mandatory document page shows both 'AS Registration' and 'CRIB Report' upload fields | When we choose the designaition Agency Head(In the personal details page) In the mandatry document page "AS Registration" field and "CRIB Report" should be available to upload the document. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_001 | AO Rejection | AO Flow §4 Approval Process | Verify HOB can resubmit an onboarding request after SMBD rejects an applicant with ARI < 30. | Functional | 1. Precondition: onboarding request with ARI < 30 raised by HOB (102117) is pending with SMBD/Sr MBD (102118) 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as HOB (102117) 5. Click Agent Management > Agent Onboarding and open the returned request 6. Correct the required information 7. On the Raise Request screen confirm Total (ARI) < 30, select PEP Question, click Raise Request and click OK 8. Verify the request returned to HOB and can be corrected and raised again | Request returns to HOB, and HOB can correct the required information and raise the request again. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_002 | AO Rejection | AO Flow §4 Approval Process | Verify AS can resubmit an onboarding request after SMBD rejects an applicant with ARI < 30. | Functional | 1. Precondition: onboarding request with ARI < 30 raised by AS (102119) is pending with SMBD/Sr MBD (102118) 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as AS (102119) 5. Click Agent Management > Agent Onboarding and open the returned request 6. Correct the required information 7. On the Raise Request screen confirm Total (ARI) < 30, select PEP Question, click Raise Request and click OK 8. Verify the request returned to AS and can be corrected and raised again | Request returns to AS, and AS can resubmit the corrected request. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_003 | AO Rejection | AO Flow §4 Approval Process | Verify LOP can resubmit an onboarding request after SMBD rejects an applicant with ARI < 30. | Functional | 1. Precondition: onboarding request with ARI < 30 raised by LOP (102043) is pending with SMBD/Sr MBD (102118) 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as LOP (102043) 5. Click Agent Management > Agent Onboarding and open the returned request 6. Correct the required information 7. On the Raise Request screen confirm Total (ARI) < 30, select PEP Question, click Raise Request and click OK 8. Verify the request returned to LOP and can be corrected and raised again | Request returns to LOP, and LOP can resubmit the corrected request. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_004 | AO Rejection | AO Flow §4 Approval Process | Verify rejection remarks entered by SMBD are available to the original requester after rejection. | Functional | 1. Precondition: onboarding request with ARI < 30 pending with SMBD 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject (enter a specific rejection remark) 4. Logout and login as the original requester (HOB/AS/LOP) 5. Open the returned request and view the rejection remarks 6. Verify the requester can identify the rejection reason entered by SMBD before resubmission | HOB/AS/LOP can identify the rejection reason and take corrective action before resubmission. |  | Not Run | High | Medium | Possible |  |  |  | Core | Yes | No | UAT
OB_REJ_005 | AO Rejection | AO Flow §3 Approval Routing | Verify an onboarding request with ARI < 30 does not move to LOP approval when SMBD rejects it. | Functional | 1. Precondition: onboarding request with ARI < 30 pending with SMBD 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as LOP (102043) and open Approval Tray 5. Login as the original requester and check the request 6. Verify the request is not in the LOP tray and is routed back to the original requester | Request remains in the rejected/returned state and is routed back to the original requester instead of LOP. |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_006 | AO Rejection | AO Flow §4 Approval Process | Verify the original requester can resubmit the request multiple times after repeated SMBD rejections. | Functional | 1. Precondition: onboarding request with ARI < 30 raised by HOB pending with SMBD 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as HOB (102117), correct and resubmit the request 5. Repeat SMBD rejection and HOB resubmission at least 3 times 6. Verify every rejection returns the request to the original requester who can correct and resubmit again | Every rejection returns the request to the original requester, who can correct and resubmit it again. |  | Not Run | High | High | Likely |  |  |  | Regression | Yes | Yes | UAT
OB_REJ_007 | AO Rejection | AO Flow §4 Approval Process | Verify LOP rejection for an onboarding request with ARI < 30 after successful SMBD approval. | Functional | 1. Precondition: onboarding request with ARI < 30 raised by HOB and approved by SMBD 2. Navigate to https://192.168.2.80:8443 3. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as HOB (102117) and open Agent Onboarding 5. Verify the request returns to the original requester for correction and resubmission | Request returns to the original HOB/AS/LOP requester for correction and resubmission. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_008 | AO Rejection | AO Flow §4 Approval Process | Verify HOB/AS/LOP can resubmit an onboarding request after LOP rejection. | Functional | 1. Precondition: onboarding request rejected by LOP 2. Navigate to https://192.168.2.80:8443 3. Login as the original requester (HOB/AS/LOP) 4. Open the returned request in Agent Onboarding and correct the information 5. On the Raise Request screen confirm Total (ARI) as calculated, select PEP Question, click Raise Request and click OK 6. Login as the next approver per ARI routing and open Approval Tray 7. Verify the request is resubmitted and follows the applicable approval flow again | Original requester can correct the request and raise it again; it follows the applicable approval flow again. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_009 | AO Rejection | AO Flow §3 Approval Routing | Verify LOP rejection does not route the request directly to Agency Admin. | Functional | 1. Precondition: onboarding request pending with LOP 2. Navigate to https://192.168.2.80:8443 3. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as AA (102186) and open Approval Tray 5. Verify the request is not in the AA tray and is returned to the original requester | Request is returned to the original requester and does not proceed to AA until LOP approves it. |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_010 | AO Rejection | AO Flow §4 Approval Process | Verify repeated LOP rejection and resubmission works correctly. | Functional | 1. Precondition: onboarding request pending with LOP 2. Navigate to https://192.168.2.80:8443 3. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Login as the original requester, correct and resubmit 5. Approve through SMBD if ARI < 30 and repeat LOP rejection/resubmission at least 3 times 6. Verify each LOP rejection returns to the requester and each resubmission reaches LOP for approval again | Each LOP rejection returns the request to the original requester, and each corrected resubmission can proceed for LOP approval again. |  | Not Run | High | High | Likely |  |  |  | Regression | Yes | Yes | UAT
OB_REJ_011 | AO Rejection | AO Flow §4 Approval Process | Verify Agency Admin rejection after LOP approval for an ARI < 30 onboarding request. | Functional | 1. Precondition: onboarding request with ARI < 30 approved by SMBD and LOP 2. Navigate to https://192.168.2.80:8443 3. Logout and login as AA (102186), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Login as the original requester and open Agent Onboarding 5. Verify the request returns to the original HOB/AS/LOP requester for correction and resubmission | Request returns to the original HOB/AS/LOP requester for correction and resubmission. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_012 | AO Rejection | AO Flow §5 Final AA Approval | Verify Agency Admin rejection does not allow the onboarding request to proceed to Agent Agreement Upload. | Functional | 1. Precondition: onboarding request pending with AA 2. Navigate to https://192.168.2.80:8443 3. Logout and login as AA (102186), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as HOB (102117) and click Submitted 5. Check whether the Edit/Agreement Upload option is available for the application 6. Verify the Agent Agreement Upload stage is not enabled until AA approves the request | Agent Agreement Upload stage is not enabled until AA approves the onboarding request. |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_013 | AO Rejection | AO Flow §4 Approval Process | Verify the original requester can resubmit an onboarding request after Agency Admin rejection. | Functional | 1. Precondition: onboarding request rejected by AA 2. Navigate to https://192.168.2.80:8443 3. Login as the original requester (HOB/AS/LOP) 4. Open the returned request, correct the information 5. On the Raise Request screen confirm Total (ARI) as calculated, select PEP Question, click Raise Request and click OK 6. Verify the request is raised again and follows the applicable approval flow | HOB/AS/LOP can correct the request and raise it again for the applicable approval flow. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_014 | AO Rejection | AO Flow §4 Approval Process | Verify repeated Agency Admin rejection and resubmission works correctly. | Functional | 1. Precondition: onboarding request pending with AA 2. Navigate to https://192.168.2.80:8443 3. Logout and login as AA (102186), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Login as the original requester, correct and resubmit 5. Approve through the required approvers again and repeat AA rejection/resubmission at least 3 times 6. Verify each rejection returns to the requester and each resubmission follows the required approval sequence | Each rejection returns the request to the original requester and each resubmission follows the required approval sequence again. |  | Not Run | High | High | Likely |  |  |  | Regression | Yes | Yes | UAT
OB_REJ_015 | AO Rejection | AO Flow §5 Final AA Approval | Verify HOB/AS/LOP can upload the Agent Agreement after AA approves the onboarding request and Sales code is genrated. | Functional | 1. Precondition: onboarding request approved by AA and sales code generated 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Submitted and click the Edit icon for the application 5. Download the Agreement, upload the signed Agreement and click Submit 6. Repeat for requests raised by AS (102119) and LOP (102043) 7. Verify the Agent Agreement Upload stage is available only after AA approval | Agent Agreement Upload stage becomes available only after successful AA approval. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_016 | AO Rejection | AO Flow §5 Final AA Approval | Verify Agent Code Activation request is not available to the AA until a valid Agent Agreement is uploaded and submitted. | Functional | 1. Precondition: onboarding request approved by AA; agreement not uploaded 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray and check for the activation request 5. Login as HOB (102117), upload the signed Agreement via Submitted > Edit and click Submit 6. Logout and login as AA (102186) and open Approval Tray 7. Verify the activation request is available to AA only after successful agreement upload | System allows activation request only after successful agreement upload. |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_017 | AO Rejection | AO Flow §5 Final AA Approval | Verify AA rejection at the Agent Code Activation stage returns the request specifically to the Agent Agreement Upload stage. | Functional | 1. Precondition: activation request with uploaded Agreement pending with AA 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray, select the activation request, enter remarks and click Reject 5. Check SMBD (102118) and LOP (102043) Approval Trays 6. Login as the requester and click Submitted 7. Verify the request returns directly to Agent Agreement Upload, not to SMBD/LOP/AA onboarding approval | Request does not return to SMBD/LOP/AA onboarding approval; it returns directly to Agent Agreement Upload. |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_018 | AO Rejection | AO Flow §5 Final AA Approval | Verify HOB can re-upload a corrected Agent Agreement after AA rejects the Agent Code Activation request. | Functional | 1. Precondition: AA rejected the Agent Code Activation request raised by HOB (102117) 2. Navigate to https://192.168.2.80:8443 3. Login as HOB (102117) 4. Click Submitted and click the Edit icon for the application 5. Upload the corrected Agent Agreement and click Submit 6. Logout and login as AA (102186) and open Approval Tray 7. Verify HOB can upload the corrected agreement and the activation request is raised again | HOB can upload the corrected agreement and raise the Agent Code Activation request again. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_019 | AO Rejection | AO Flow §5 Final AA Approval | Verify AS can re-upload a corrected Agent Agreement after AA rejects the Agent Code Activation request. | Functional | 1. Precondition: AA rejected the Agent Code Activation request raised by AS (102119) 2. Navigate to https://192.168.2.80:8443 3. Login as AS (102119) 4. Click Submitted and click the Edit icon for the application 5. Upload the corrected Agent Agreement and click Submit 6. Logout and login as AA (102186) and open Approval Tray 7. Verify AS can upload the corrected agreement and the activation request is raised again | AS can upload the corrected agreement and resubmit the activation request. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_020 | AO Rejection | AO Flow §5 Final AA Approval | Verify LOP can re-upload a corrected Agent Agreement after AA rejects the Agent Code Activation request. | Functional | 1. Precondition: AA rejected the Agent Code Activation request raised by LOP (102043) 2. Navigate to https://192.168.2.80:8443 3. Login as LOP (102043) 4. Click Submitted and click the Edit icon for the application 5. Upload the corrected Agent Agreement and click Submit 6. Logout and login as AA (102186) and open Approval Tray 7. Verify LOP can upload the corrected agreement and the activation request is raised again | LOP can upload the corrected agreement and resubmit the activation request. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_021 | AO Rejection | AO Flow §5 Final AA Approval | Verify repeated AA rejection at Agent Code Activation stage allows repeated agreement correction and resubmission. | Functional | 1. Precondition: activation request pending with AA 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) and reject the activation request 4. Login as the requester and re-upload a corrected Agreement 5. Repeat rejection and re-upload at least 3 times 6. Approve the final submission as AA 7. Verify each rejection returns to Agreement Upload and the requester can resubmit until AA approval | Each rejection returns to Agreement Upload, allowing the requester to correct and resubmit until AA approval. |  | Not Run | High | High | Likely |  |  |  | Regression | Yes | Yes | UAT
OB_REJ_022 | AO Rejection | AO Flow §5 Final AA Approval | Verify AA approval after a previously rejected Agent Code Activation request activates the Agent Code. | Functional | 1. Precondition: activation request previously rejected by AA and corrected Agreement resubmitted 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray, select the activation request and click Approve 5. Logout and login with the agent code 6. Verify the Agent Code is activated successfully | After corrected agreement submission and AA approval, Agent Code is successfully activated. |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_023 | AO Rejection | AO Flow §5 Final AA Approval | Verify the agent cannot log in when AA rejects the final Agent Code Activation request. | Functional | 1. Precondition: activation request pending with AA 2. Navigate to https://192.168.2.80:8443 3. Login as AA (102186) 4. Open Approval Tray, select the activation request, enter remarks and click Reject 5. Logout and attempt to login with the agent code 6. Verify the Agent Code remains inactive and the agent cannot log in | Agent Code remains inactive and the agent cannot log in until AA provides final approval. |  | Not Run | Critical | Critical | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_024 | AO Rejection | AO Flow §3 Approval Routing | Verify an ARI > 30 request skips SMBD approval even after subsequent rejection/resubmission cycles. | Functional | 1. Precondition: onboarding request with ARI > 30 raised by HOB 2. Navigate to https://192.168.2.80:8443 3. Reject the request at LOP (102043) and resubmit as HOB 4. Approve at LOP and reject at AA (102186), then resubmit as HOB 5. After each resubmission check SMBD (102118) Approval Tray 6. Verify the request goes directly to LOP each time and SMBD approval is never introduced | Request goes directly to LOP; SMBD approval is not introduced into the workflow. |  | Not Run | Critical | Critical | Likely |  |  |  | Regression | Yes | Yes | UAT
OB_REJ_025 | AO Rejection | AO Flow §4 Approval Process | Verify LOP rejection for an ARI > 30 request returns it to the original HOB/AS/LOP requester. | Functional | 1. Precondition: onboarding request with ARI > 30 pending with LOP 2. Navigate to https://192.168.2.80:8443 3. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Login as the original requester (HOB/AS/LOP) 5. Verify the original requester receives the rejected request and can correct and resubmit it | Original requester receives the rejected request and can correct and resubmit it. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_026 | AO Rejection | AO Flow §4 Approval Process | Verify Agency Admin rejection for an ARI > 30 request returns it to the original HOB/AS/LOP requester. | Functional | 1. Precondition: onboarding request with ARI > 30 approved by LOP, pending with AA 2. Navigate to https://192.168.2.80:8443 3. Logout and login as AA (102186), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Login as the original requester and click Submitted 5. Verify the request returns to the original requester and does not proceed to Agent Agreement Upload | Request returns to the original requester and does not proceed to Agent Agreement Upload. |  | Not Run | High | High | Possible |  |  |  | Core | Yes | Yes | UAT
OB_REJ_027 | AO Rejection | AO Flow §3 Approval Routing | Verify repeated rejection/resubmission for an ARI > 30 request follows LOP -> AA approval flow without involving SMBD. | Functional | 1. Precondition: onboarding request with ARI > 30 2. Navigate to https://192.168.2.80:8443 3. Reject at LOP (102043), resubmit, approve at LOP and reject at AA (102186) 4. Resubmit again as the original requester 5. Track the Approval Tray of SMBD, LOP and AA after each resubmission 6. Verify every corrected resubmission goes to LOP first, then AA after LOP approval, without SMBD | Every corrected resubmission goes to LOP first and then AA after LOP approval. |  | Not Run | High | High | Likely |  |  |  | Regression | Yes | Yes | UAT
OB_REJ_028 | AO Rejection | AO Flow §4 Approval Process | Verify the original requester is retained throughout all rejection and resubmission cycles. | Functional | 1. Precondition: three onboarding requests raised by HOB (102117), AS (102119) and LOP (102043) respectively 2. Navigate to https://192.168.2.80:8443 3. Reject each request at SMBD/LOP/AA stages across multiple cycles 4. After each rejection login as each role and check returned requests 5. Verify every rejection returns to the same original requester for resubmission | Whether HOB, AS, or LOP originally raised the request, every rejection is returned to that same requester for resubmission. |  | Not Run | High | High | Likely |  |  |  | Regression | Yes | Yes | UAT
OB_REJ_029 | AO Rejection | AO Flow §4 Approval Process | Verify rejection remarks are retained for each rejection cycle. | Functional | 1. Precondition: onboarding request raised by HOB 2. Navigate to https://192.168.2.80:8443 3. Reject at SMBD with remark 'R1', resubmit; reject at LOP with remark 'R2', resubmit; reject at AA with remark 'R3' 4. Logout and login as HOB (102117) and open the returned request 5. View the rejection remarks history 6. Verify each rejection cycle retains the applicable approver's remarks | Each rejection contains the applicable approver's remarks, allowing the requester to understand the reason for rejection. |  | Not Run | Medium | Medium | Likely |  |  |  | Regression | Yes | No | UAT
AO_NOTIF_001 | AO Notification | TS: Approvals | Verify notifications are triggered when an onboarding application moves to the next approval role | Integration | 1. Precondition: onboarding request with ARI < 30 raised by HOB 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Approve 4. Logout and login as LOP (102043) 5. Open the notification panel (bell icon) 6. Verify a notification is triggered to the next-level approver when the application moves to the next stage | Notification is triggered to the next-level approver when the application moves to the next approval stage |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
AO_NOTIF_002 | AO Notification | TS: Approvals | Verify notifications are triggered when SMBD approves and the application moves to LOP | Integration | 1. Precondition: onboarding request with ARI < 30 pending with SMBD 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Approve 4. Logout and login as LOP (102043) 5. Open the notification panel (bell icon) 6. Verify LOP receives an approval action notification | LOP receives an approval action notification. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
AO_NOTIF_003 | AO Notification | TS: Approvals | Verify notifications are triggered when LOP approves and the application moves to AA | Integration | 1. Precondition: onboarding request pending with LOP 2. Navigate to https://192.168.2.80:8443 3. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Approve 4. Logout and login as AA (102186) 5. Open the notification panel (bell icon) 6. Verify AA receives an approval action notification | AA receives an approval action notification. |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
AO_NOTIF_004 | AO Notification | TS: Approvals | Verify rejection notification is triggered when SMBD rejects the application | Integration | 1. Precondition: onboarding request with ARI < 30 raised by HOB, pending with SMBD 2. Navigate to https://192.168.2.80:8443 3. Logout and login as SMBD/Sr MBD (102118), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as HOB (102117) 5. Open the notification panel (bell icon) 6. Verify the original requester receives the rejection notification containing the applicant name | Original requester receives the rejection notification containing the applicant name. |  | Not Run | Medium | Medium | Possible |  |  |  | Integration | Yes | No | UAT
AO_NOTIF_005 | AO Notification | TS: Approvals | Verify rejection notification is triggered when LOP rejects the application | Integration | 1. Precondition: onboarding request raised by HOB, pending with LOP 2. Navigate to https://192.168.2.80:8443 3. Logout and login as LOP (102043), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as HOB (102117) 5. Open the notification panel (bell icon) and open Agent Onboarding 6. Verify the requester receives the rejection notification and the application is available for correction/resubmission | Original requester receives the rejection notification and the application is available to the requester for correction/re-submission |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
AO_NOTIF_006 | AO Notification | TS: Approvals | Verify rejection notification is triggered when AA rejects the application | Integration | 1. Precondition: onboarding request raised by HOB, pending with AA 2. Navigate to https://192.168.2.80:8443 3. Logout and login as AA (102186), open Approval Tray, select the application by generated Sales Code, click Next up to the Average Recruitment Indicator screen, enter remarks and click Reject 4. Logout and login as HOB (102117) 5. Open the notification panel (bell icon) and open Agent Onboarding 6. Verify the requester receives the rejection notification and the application is returned for the applicable next action | Original requester receives the rejection notification and the application is returned to the requester for the applicable next action |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
AO_NOTIF_007 | AO Notification | TS: Approvals | Verify notifications are sent only to the correct users based on the workflow stage | Integration | 1. Precondition: onboarding request with ARI < 30 raised by HOB 2. Navigate to https://192.168.2.80:8443 3. Approve at SMBD (102118); check notifications for LOP (102043), AA (102186) and AS (102119) 4. Reject at LOP; check notifications for HOB, AA and AS 5. Compare recipients against the workflow stage 6. Verify only the current approver receives action notifications, the requester receives rejection notifications and unrelated users receive none | Requester receives notification when application gets rejeceted, while the role responsible for the current approval receives the action notification; unrelated users do not receive the notification |  | Not Run | Medium | Medium | Likely |  |  |  | Integration | Yes | No | UAT
AO_NOTIF_008 | AO Notification | TS: Approvals | Verify notification status is correctly recorded and duplicate notifications are not generated for a single workflow transition | Integration | 1. Precondition: onboarding request with ARI < 30 raised by HOB 2. Navigate to https://192.168.2.80:8443 3. Perform one approval transition (SMBD approve) 4. Logout and login as LOP (102043) 5. Open the notification panel (bell icon) and count notifications for the application 6. Refresh the page and re-login to confirm the notification count is unchanged 7. Verify each workflow transition generates the expected notification only once | Each workflow transition generates the expected notification only once. |  | Not Run | Medium | Medium | Possible |  |  |  | Integration | Yes | No | UAT

## Lists
Test Type | Business Criticality | Impact | Likelihood | Scope Category | Status | Priority | Yes/No | Environment | Release | Requirement Type
Functional | Low | Low | Rare | Core | Not Run | P1 | Yes | DEV | Release 1 | Functional
Regression | Medium | Medium | Unlikely | Impacted | Pass | P2 | No | QA | Release 2 | Non-Functional
Integration | High | High | Possible | Regression | Fail | P3 |  | UAT | Release 3 | Technical
API | Critical | Critical | Likely | Integration | Blocked | P4 |  | Production |  | Business
UI |  |  | Almost Certain | Security | Not Applicable
Mobile |  |  |  | Performance
Performance |  |  |  | Optional
Security |  |  |  | Out of Scope
UAT
Smoke
Sanity
Note: Scope category descriptions
Core – Mandatory functionality
Impacted – Directly affected by the change
Regression – Existing functionality potentially affected
Integration – External/system integration
Security – Security-sensitive functionality
Performance – Performance-sensitive functionality
Optional – Lower-priority validation
Out of Scope – Explicitly excluded with justification
Testcase column color code
Manual Entry
Dropdown Selection
Values Based on Calculation